## Dev
Sr. No | Name of module | Sub Module | Priority | Estimated time | Start Date | End Date | Development Status | Testing Status | Notes
1 | When the Doctor Exits the patient then he need to make a Patient Flow- |  |  | 3 days | 2015-05-12 | 2015-05-15 | done |  | 2 days modyfify according to Dr Jain
1. Reports/Tests
2. Review (by doctor)
3. dietitian
4. Pharma
5. Insulin training
2 | Integration of CSU |  |  | 3 days |  |  | done
1. Billing (based on reports/tests)
2. Report/test result uploaded into system
3. Exit from report and inbound into Doctor reporting screen. If doctor does not want to see the patient he can forward to other departmetn like diet, insulin training. Exit from CSU
3 | Need to Create User Group on the Basis of Priority (fast Clearance) |  |  | 1 day |  |  | done
1. Group by time taken icons
4 | Popup should come to doctor related to Urgent patients after 30 mins. |  |  | 3 hours |  |  | done
1. Alert system if wait time exceeds 30 minutes at one station
5 | Preference Criteria Related to patient
1. Old Patient = Same doctor (if)
2. Female = Female
3. Male = Male
6 | Doctor Feedback/Comment column should be there related to time: |  |  | 1 day
1. If today = Same Doctor/ Other
2. Time Less then 1, < 2, < 3, < 5 and more then 5 (minutes)
7 | Which consultant is required to plan treatement? |  |  | 1 day
8 | Doctor clearance list
|  | 1. If Doctor want to Clear their patient they will put them into clearance list ( as a reminder, patient needs to be checked before he lives the total facility) Same as clearing list, some more lists should be there: 1. Email list 2. Phone list 3. Post list | [6 empty] | Need to discuss
9 | Help Desk |  |  | 1 day
Operation manager Role - who will done all the listed task asigned by Doctor to patient
10 | Information sections: Basic details - referred by info | [7 empty] | Already exist
Basic detail section, add one field - referred by info
11 | Basic History of patient
|  | Diabetes duration : How diabetes was diagnosed: Healthy weight : Change in body weight : kg , increase / decrease and duration Family history of Diabetes : Height Weight BMI BP Positive finding in examination | [6 empty] | Some info already taken
12 | Meal pattern INFO | pre defined options with time of meal : to be completed by dietician or health station , if edited old meal pattern will go in history and new will be visible . | [6 empty] | Field is not clear
13 | Complaints list | Complaints list on the visit day : name of complaint and duration . select complaints to treat : tick box, only selected complaints will be used for prescription creation | [6 empty] | Need to discuss
14 | Report Generation: Graphs
|  | Analysis by our software : visit date wise : BP graph, HbA1C graph, Creatinine and eGFR graph, e GFR calculation by software, Weight graph , medication analysis table |  | 5 days |  |  |  |  | Need to discuss about HbA1C graph, Creatinine and eGFR graph, e GFR calculation by software
15 | Other sections |  |  | 2 days
Diet plan : by system Diabetes education : options list Exercise recommendation : options list
16 | Drug intake with Meal option | [7 empty] | Need to discuss fiels are not clear
drugs will be as per empty stomach, BF, L and dinner time etc
19 | Design a prescription format | [7 empty] | Basic prescription pad already exist
Glycemic control treatment : oral drugs first, name of drug, time and relation to meal, dose. Insulin after oral drug list is completed and will include name of insulin, dose in units, time and relation to meals -HT management : name of drug, dose, time and relation to meals -Is lipid management indicated : if yes, name of drug, dose, time and relation to meals -Complication management : name of drug, dose, relation to meals, duration -Other disease management : name of drug, time, relation to meals, duration -Symptomatic management : name of drug, dose, time and relation to meal, duration
20 | PRESCRIPTION to be visible to pharmacy | [7 empty] | Internal pharmacy is aleady exist
21 | Diabetes type | [7 empty] | Need to discuss
HT
Dyslipidemia
Others
22 | Knowledge Center | [7 empty] | Advance feature implement later and some RND is required
Sharing of knowledge between Totall facility and outside doctors
23 | Diet Plan | [7 empty] | Need to discuss
Refer meal pattern info
24 | Photo's through Device | [7 empty] | Advance feature implement later and some RND is required
Image capture through device like mobile phone, camera, scanner
25 | Integration of IPD | [7 empty] | Advance feature implement later and some RND is required

## UAT
Sr. No. | Module & Sub Module | UAT Status | Integrated in Production